## Taskliste
Code Taskliste
				1	Prototyp
				2	Alpha			Not needed	Open	On Going	Done
				3	Beta		insert ...	-	1	2	3

	Object	Category	Editor	Priority	Status	Complexity	Stunden	Risks	Description	Basic function	Engine Integration	Function checked
	Gesten	Hit	Denis	2	1	40	2		Attack a Enemy
	Gesten	Lift up	Denis	2	1	40	2		Lift up a virtual object
	Gesten	Move	Denis	2	1	40	2		Move a virtual object
	Gesten	Throw	Denis	2	1	40	2		Throw a virtual object
	Gesten	Pick Up	Denis	1	1	50	3		Pick up the key or key parts
	Gesten	Open	Denis	1	1	50	3		Open the door
	Gesten	Jump	Denis	3	1	70	4		recognized the real player jumped
	Gesten	Climb	Denis	3	1	70	4		Climb out of liquid

	Scan	Scanning	Lukas	2	1	80	10		Scan the enviroment, Panoramaview
	Scan	User date	Lukas	2	1	30	1		Get user hight and user chest- or eyehight + ask if he scans with chest- or eyehight
	Scan	Save user input	Lukas	nice to have	1	25	2		Saves different user inputs for there hight etc.
	Scan	Generate collison body	Lukas	2	1	45	3		Generate the collison body for collision in the virtual world
	Scan	Save scan data	Lukas	2	1	50	5		Save the data for the generation of random levels

	UI	Main menu	Denis	2	1	10	2		Main menu (Levelselect, random generated Level,Option, Userinput, Quit)
	UI	Option menu	Lukas	2	1	10	2		Difficulty, Themes, Soundvolume
	UI	Levelselect	Lukas	2	1	10	1		Level 1, Level 2, Level 3
	UI	User input data	Lukas	2	1	10	1		UI for the User to input or select his Data
	UI	Scanning	Lukas	2	1	10	1		UI while Scanning, Progress etc.
	UI	Random generate	Lukas	2	1	10	1		UI while gerating random Level, Progress etc.
	UI	Credits	Lukas	3	1	10	5		Shows the credits
	UI	Ingame	Denis	2	1	10	1		Player hit
	UI	Ingame	Denis	2	1	10	1		win
	UI	Ingame	Denis	2	1	10	1		Lose (die)
	UI	Ingame	Denis	2	1	10	1		pause menu with quit, resume or restart level
	UI	Ingame	Denis	2	1	10	1		out of synch message
	UI	Ingame	Denis	2	1	10	2		shows the synch spot
	UI	Ingame	Denis	2	1	10	1		shows player HP
	UI	Ingame	Denis	2	1	10	1		keycount, if keyparts or the full key
	UI	Ingame	Denis	2	1	10	1		timer
	UI	Ingame	Denis	2	1	10	1		enemy HP
	UI	Tutorial	Lukas	3	1	50	5		Explains the features to the player

	Level	Tutoriallevel	Lukas	3	1	50	6		Shows all features to the user in a simple to follow level
	Level	Level 1	Lukas	1	1	40	4		Easy level, premade
	Level	Level 2	Lukas	2	1	50	5		Medium level, premade
	Level	Level 3	Lukas	2	1	60	5		Hard Level, premade
	Level	Generate level from scanned data	Lukas	2	1	80	15		Generate a random level from the data
	Level	Generate difficulty from data	Lukas	3	1	80	15		Generate the difficulty for the level from the data
	Level	Generate theme from data	Lukas	3	1	30	4		Generate the theme for the level from the data
	Level	Different Themes	Lukas	3	1	20	4		Natur (Spring, summer, autumn, winter), Ghosthous, Sci-fi, Kindergarden, medieval and modern living style

	Enemy	Air enemy AI	Lukas	2	1	60	5		Fly around and attack player
	Enemy	Ground enemy AI	Lukas	2	1	30	5		Walk around and attack player
	Enemy	Enemy getting hit	Lukas	2	1	20	2		Enemy is getting hit, loses health
	Enemy	Enemy dies	Lukas	2	1	20	2		Enemy dies from player attacks

	Obstacle	Normal obstacle	Lukas	1	1	30	3		Normal obstacle, where the player cant go through
	Obstacle	Damaging obstacle	Lukas	2	1	40	3		Damagin obstacle, where the player cant go through (Spices)
	Obstacle	Normal liquid	Lukas	2	1	50	4		Water, where the can fall into, put has to walk out of, slows him
	Obstacle	Damaging liquid	Lukas	2	1	60	4		Damaging liquid, damages the player every 2 seconds

	Player	Synche ingame body with camera movement	Denis	1	1	60	6		when the real camera moves, the ingame body moves to
	Player	Collsion with obstacle	Denis	1	1	40	3		when the player walks against a obstacle, warning (message + vibrating) because of the out of synch, Level pauses until resynch
	Player	Resynch camera	Denis	1	1	60	3		synchs the real camera with the ingame body again, levels resumes
	Player	show the resynch spot	Denis	1	1	20	3		shows the spot to resynch after a obstacle collision or after a restart
	Player	HP	Denis	2	1	10	1		the HP of the Player ( 3 HP)

	Ingame	Win	Denis	1	1	10	1		player has the key and opens the door
	Ingame	Lose	Denis	2	1	10	1		no HP left, quit or restart level
	Ingame	Door opens	Denis	2	1	10	2		the door opens, to show that the player won
	Ingame	Throwing Puzzel	Denis	2	1	40	5		the flies in the air and the player can shoot it down with objects or build a tower to grab it. Hte key is hold by a balloon
	Ingame	Trowing objects for throwing puzzle	Denis	2	1	30	2		respawning sharp objects to throw and the key in the air
	Ingame	Multikey Puzzel	Denis	2	1	30	3		multiple key parts are hidden in the level, the player has to collect all of them to create to key
	Ingame	Key under other object	Denis	1	1	40	5		hid the key onder virtual or real objects
	Ingame	Handoverlay	Denis	2	1	50	5		the hand gets a texture overlay so it fitts in the virtual world

	Music	Ingame	Lukas	2	1	10	3
	Music	Main menu	Denis	2	1	10	1
	Music	Tutorial	Lukas	2	1	10	1
	Music	Scanning	Lukas	2	1	10	1

	Sound	Air enemy fly	Lukas	2	1	10	1
	Sound	Air enemy attack	Lukas	2	1	10	1
	Sound	Air enemy getting hit	Lukas	2	1	10	1
	Sound	Air enemy dies	Lukas	2	1	10	1
	Sound	Ground enemy walk	Lukas	2	1	10	1
	Sound	Ground enemy attack	Lukas	2	1	10	1
	Sound	Ground enemy getting hit	Lukas	2	1	10	1
	Sound	Ground enemy dies	Lukas	2	1	10	1
	Sound	Punch enemy	Denis	2	1	10	1
	Sound	pick up key	Denis	2	1	10	1
	Sound	camera out of synch	Denis	2	1	10	1
	Sound	resynch camera	Denis	2	1	10	1
	Sound	Player getting hit	Denis	2	1	10	1
	Sound	Player win	Denis	2	1	10	1
	Sound	Player lose	Denis	2	1	10	1
	Sound	Player in liquid	Denis	2	1	10	1
	Sound	thowing object respawn	Denis	2	1	10	1
	Sound	ballon hit	Denis	2	1	10	1
	Sound	Scanning succes	Lukas	2	1	10	1
	Sound	Scanning failed	Lukas	2	1	10	1

					224

## Soundliste
Sound-liste

					Not needed	Open	On Going	Done
					insert ...	-	1	2	3

	Sound	Soundtype	Editor	Priority	Status	Autor	Source
Ingame	Spring	Music	Lukas	2	1				The ingame backgroundmusic should fit the theme
Ingame	Summer	Music	Lukas	3	2
Ingame	Autumn	Music	Lukas	3	3
Ingame	Winter	Music	Lukas	3	4
Ingame	Sci-Fi	Music	Lukas	3	5
Ingame	Ghosthous	Music	Lukas	3	6
Ingame	Kindergarden	Music	Lukas	3	7
Ingame	modern living style	Music	Lukas	3	8
Ingame	medieval	Music	Lukas	3	9
	Main menu	Music	Denis	2	1
	Tutorial	Music	Lukas	2	1
	Scanning	Music	Lukas	2	1

	Air enemy fly	Sound	Lukas	2	1
	Air enemy attack	Sound	Lukas	2	1
	Air enemy getting hit	Sound	Lukas	2	1
	Air enemy dies	Sound	Lukas	2	1
	Ground enemy walk	Sound	Lukas	2	1
	Ground enemy attack	Sound	Lukas	2	1
	Ground enemy getting hit	Sound	Lukas	2	1
	Ground enemy dies	Sound	Lukas	2	1
	Punch enemy	Sound	Denis	2	1
	pick up key	Sound	Denis	2	1
	camera out of synch	Sound	Denis	2	1
	resynch camera	Sound	Denis	2	1
	Player getting hit	Sound	Denis	2	1
	Player win	Sound	Denis	2	1
	Player lose	Sound	Denis	2	1
	Player in liquid	Sound	Denis	2	1
	thowing object respawn	Sound	Denis	2	1
	ballon hit	Sound	Denis	2	1
	Scanning succes	Sound	Lukas	2	1
	Scanning failed	Sound	Lukas	2	1

## Assetliste
Asset-Liste

					Not needed	Open	On Going	Done
					insert ...	-	1	2	3

	Asset	Type	Editor	Priority	Status	Autor	Source	Duration “Manntage”	Description		Engine Integration	Function checked
	Air Enemy Spring		Lukas	2	1			1
	Air Enemy Summer		Lukas	3	1			1
	Air Enemy Autumn		Lukas	3	1			1
	Air Enemy Winter		Lukas	3	1			1
	Air Enemy Sci-Fi		Lukas	3	1			1
	Air Enemy Ghosthouse		Lukas	3	1			1
	Air Enemy Medieval		Lukas	3	1			1
	Air Enemy Kindergarden		Lukas	3	1			1
	Ground Enemy Spring		Lukas	2	1			1
	Ground Enemy Summer		Lukas	3	1			1
	Ground Enemy Autumn		Lukas	3	1			1
	Ground Enemy Winter		Lukas	3	1			1
	Ground Enemy Sci-Fi		Lukas	3	1			1
	Ground Enemy Ghosthouse		Lukas	3	1			1
	Ground Enemy Medieval		Lukas	3	1			1
	Ground Enemy Kindergarden		Lukas	3	1			1

	Key		Denis	1	1			1
	Key parts		Denis	2	1			1
	Theme keytexture		Denis	3	1			4	Theme Textures
	Object to throw		Denis	2	1			1

	Spring Texture		Lukas	2	1			1	For the overlay of real objects to fit the theme
	Summer Texture		Lukas	3	1			1	For the overlay of real objects to fit the theme
	Autumn Texture		Lukas	3	1			1	For the overlay of real objects to fit the theme
	Winter Texture		Lukas	3	1			1	For the overlay of real objects to fit the theme
	Sci-Fi Texture		Lukas	3	1			1	For the overlay of real objects to fit the theme
	Ghosthouse Texture		Lukas	3	1			1	For the overlay of real objects to fit the theme
	Medieval Texture		Lukas	3	1			1	For the overlay of real objects to fit the theme
	Kindergarden Texture		Lukas	3	1			1	For the overlay of real objects to fit the theme
	Modern Texture		Lukas	3	1			1	For the overlay of real objects to fit the theme

	Normal Box		Lukas	1	1			1	Theme Textures
	Normal Wall		Lukas	1	1			2	Theme Textures
	Liquid (water)		Lukas	2	1			2	Water
	Liquid (damaging)		Lukas	2	1			2	Theme Textures
	Spikes (Stacheln)		Lukas	2	1			2	Theme Textures

	Handoverlay Texture		Denis	2	1			3	A Asset/Texture to put over the hand so it is part of the virtual world

					44